## Instructions
Congratulations on beginning your community coalition!
This Standards document serves as a check-list for forming and launching your community coalition.
Review all the standards on the Formation Standards tab and work with your local Health Department to answer any questions you may have and outline a process for achieving each standard.
Other Resources
Coalition Launch Facilitator Guide | A more detailed agenda for the coalition launch meeting in Standard 4. To be reviewed by the meeting facilitator and/or chair.
Coalition Launch Meeting Power Point | Use this power point presentation to run your Coalition Launch meeting outlined in "Standard 4: Organize and structure the coalition."
Coalition Launch Agenda Template | A template for the coalition launch meeting agenda in Standard 4.
Coalition Launch Minutes Template | A template for taking notes during the meeting in Standard 4 (or any coalition meeting).
Coalition Resources | Links to several useful websites for running a community coalition.
Workgroup Descriptions | A handout that describes the workgroups, used in the coalition launch meeting.

## Formation Standards
Coalition Formation Phase
Standard | Task | Details | Status | Coalition Notes
1. Organize the Community
| 1. Identify one person to coordinate initial activities | The coordinating person will keep momentum going and ensure the correct steps are being taken during the formation phase
| 2. Identify a key leader to act as a champion | A key leader is a person with influence and connections in the community. They make decisions for their agencies and communities, including funding, policy, and prioritization decisions. Mayors, school principles, superintendents, police chiefs, church leaders, community leaders, service provider executive directors, etc. This person will help bring others on board and act as a champion for the coalition.
| 3. Identify a lead agency | The lead agency is formal organization like a city government, a school district, or a nonprofit organization that can hire the facilitator and provide financial support, staffing, office support, office space, meeting rooms, and other resources.
| 4. Develop a list of key leaders | The more key leaders on your list, the better. Consider which populations and organizations need to be involved to help the coalition succeed.
| 5. Outline what a key leader is and how they work with the coalition | Clearly identify in writing what a key leader is and their role working with the coalition. Key leaders may connect the coalition with members and other leaders; find resources such as meeting space or grants; identify risks; and support strategies and programs. Key leaders are people with influence in the community and beyond who champion and support the coalition.
| 6. Define the community | Is the community defined by city boundaries? School boundaries? A group of neighborhoods? Etc.
| 7. Identify the 'why' behind bringing the coalition together | Why are you bringing people together into a coalition? Why are others coming to the table? Understand the initial motivation but do not yet start prioritizing your goals.
| 8. Decide whether this is a new initiative or whethe there are existing efforts you can join. | Research if there are other similar efforts already underway in your community. If so, can you join forces with them? Become a subcommittee? Or is this a new initiative?
| 9. Identify and find any needed resources for coalition formation | Ideally, funds could be found to hire a coalition coordinator. Other expenses could be donated, such as space to meet, basic meeting materials, food for meetings, etc.
2. Identify the community's readiness to form a coalition and resolve any readiness issues
| 1. Learn about the issues and the community: public health, community coalitions, prevention, the local community | Learn about the community's population, major strengths, demographics, languages, education levels, etc. Learn about the public health model, community coalitions, prevention science. Use the power point slides in the Coalition Launch meeting as well as the resources listed in Appendix B.
| 2. Talk within the coalition and to a few key leaders or stakeholders: a) Educate the community about public health and community coalitions. b) Explore how the community feels about collaborating in a coalition. | Speak to your coalition members about what they have learned about public health, coalitions, prevention, etc. 1) Do you all feel this type of collaborative effort will be successful in your community? 2) Are there any barriers you may need to overcome first? 3) Has the community ever collaborated before? How did that go? Were there turf wars, or large personalities that did not want to work as a team? 4) Ask questions about whether the community is ready to face hard truths and work through them together. Ask these same questions to your key leaders and stakeholders; you may need to help them understand how coalitions work and why they're important. Try to also speak with diverse populations in your community.
| 3. Based on your discussions, identify any readiness issues and outline steps to resolve the issues | Readiness issues are barriers or problems that could get in the way of the coalition succeeding. Differentiate between deal breakers that need to be addressed now and smaller issues that can be addressed as you continue through the coalition process. Consider whether you need support from partners or stakeholders who could help you think the problems through and brainstorm solutions.
| 4. Decide which coalition framework to utilize. | It is recommended to use an evidence-based or research-based framework such as Communities That Care, CADCA model, or Coalitions Lite. Work with your local Health Department to understand the differences and discuss with the group which framework will work best for your community.
3. Engage key leaders
| 1. Meet with key leaders and find at least three who can commit to helping to build and develop the coalition | Review key leader roles from step 1.5. Commitment from each key leader on what they can / cannot do. Also ask them for any ideas for potential coalition members, asking specifically about diverse populations and agencies that could help with the work. This conversation could be done at the same time as your readiness conversations above.
| 2. Outline when coalition will communicate with key leaders for feedback, updates, and requests | Quick conversation in coalition
4. Organize and structure the coalition
| 1. Identify a list of potential coalition members | Consider community stakeholders (individuals and populations who will be affected by the coalition's efforts), making sure to include diverse populations in the community, agencies that could help do the work, and recommendations from key leaders. Aim to represent all 12 sectors, including youth, plus a high percentage of residents. Your membership may grow steadily, so integrate recruitment into your efforts moving forward.
| 2. Draft a brief elevator speech for recruitment | Consider: 1) why [Standard 1.7.], 2) how a coalition operates, 3) role of coalition members, and 4) time commitment.
| 3. Recruit a diverse, representational list of community coalition members. | Recruitment will be an ongoing process, but start by meeting with lots of different people, attending community events, and reaching out to potential partners. All existing coalition members and key leaders can help with recruitment.
| 4. Hold first coalition meeting. Agenda includes: | Use the Coalition Launch Power Point and Facilitator Guide to walk you through the meeting. There are also templates for the participants' agenda and meeting minutes.
| Train members on coalition frameworks / process and coalition approval of initial timeline. | Included in the power point.
| Clarify members' roles and responsibilities. | Explain clearly the difference between Key Leaders, Coalition Members, and Stakeholders. Included in the power point.
| Elect a coalition chair, co-chair, and secretary. | Included in the power point.
| Brainstorm a coalition name. | Included in the power point.
| Establish initial workgroups and have each coalition member select at least one workgroup to participate on. Select workgroup chairs. | Included in the power point.
| Brainstorm initial ideas for a vision statement. | Included in the power point.
| Assign initial tasks to workgroup, including: | Included in the power point.
| Draft a vision statement with initial ideas from the meeting, plus input from key leaders and stakeholders; share with community | Ad Hoc vision workgroup
| Develop a recruitment plan for new members, paying special attention to diversity | Recruitment and Outreach workgroup
| Develop an orientation packet for new members | Board Development workgroup
| Start outlining policies and procedures, including decision-making and voting processes, how to vote in new members, quorums, etc. | Board Development workgroup
5. Workgroups meet and complete their assigned tasks
6. Share any meeting outcomes with Key Leaders or Stakeholders
Your coalition is now officially formed and on its way! Proceed to your selected coalition framework for next steps.

## Dropdown Lists (hidden)
Status
Complete
In Progress
Not Started